## Schedule
구디아카데미 멘토링 프로젝트 개발 일정
By Task
WBS | WBS | Task | Days | Developer | Start Date | Finish Date | Status | Progress | Remain | Comments | Holiday
1.1 |  | 분석 설계 | 17 |  | 2023-01-10 | 2023-01-16 |  |  | 0 |  | 2023-01-21
1.1 | 1 | WBS 작성 | 5 | 1조 전체 | 2023-01-10 | 2023-01-16 | CLOSE | 100% | 0 |  | 2023-01-22
1.1 | 2 | 데이터 테이블 분석 | 4 | 1조 전체 | 2023-01-10 | 2023-01-13 | CLOSE | 100% | 0 |  | 2023-01-23
1.1 | 3 | 화면 설계서 분석 | 4 | 1조 전체 | 2023-01-10 | 2023-01-13 | CLOSE | 100% | 0 |  | 2023-01-24
1.1 | 4 | Framework 개발 및 환경 구축 | 4 | 1조 전체 | 2023-01-10 | 2023-01-13 | CLOSE | 100% | 0
1.2 |  | MES기준정보관리 | 16 |  | 2023-01-17 | 2023-01-20 |  |  | 16
1.2 | 1 | 품번관리 | 2 | 유기현 | 2023-01-17 | 2023-01-18 |  | 0% | 2
1.2 | 2 | BOM관리 | 2 | 김재형 | 2023-01-17 | 2023-01-18 |  | 0% | 2
1.2 | 3 | 공정관리 | 2 | 유기현 | 2023-01-19 | 2023-01-20 |  | 0% | 2
1.2 | 4 | 창고관리 | 2 | 정민영 | 2023-01-17 | 2023-01-18 |  | 0% | 2
1.2 | 5 | 작업지시관리 | 2 | 김재형 | 2023-01-19 | 2023-01-20 |  | 0% | 2
1.2 | 6 | 공통코드관리 | 2 | 서지환 | 2023-01-17 | 2023-01-18 |  | 0% | 2
1.2 | 7 | 설비등록 | 2 | 정민영 | 2023-01-19 | 2023-01-20 |  | 0% | 2
1.2 | 8 | 검사 항목 설정 | 2 | 서지환 | 2023-01-19 | 2023-01-20 |  | 0% | 2
1.2 | 9 | 안전재고 | 2 | 정민영 |  | 1900-01-01 |  | 0% | 2
1.3 |  | 보안 | 8 |  | 2023-01-17 | 2023-01-30 |  |  | 8
1.3 | 1 | 사용자 등록 | 2 | 김민식 | 2023-01-17 | 2023-01-18 |  | 0% | 2
1.3 | 2 | 사용자 그룹 설정 | 2 | 김민식 | 2023-01-19 | 2023-01-20 |  | 0% | 2
1.3 | 3 | 기능 등록 | 2 | 김민식 | 2023-01-25 | 2023-01-26 |  | 0% | 2
1.3 | 4 | 기능 권한 관리 | 2 | 김민식 | 2023-01-27 | 2023-01-30 |  | 0% | 2
1.4 |  | 영업관리 | 4 |  | 2023-01-25 | 2023-01-26 |  |  | 4
1.4 | 1 | 제품 주문 | 2 | 정민영 | 2023-01-25 | 2023-01-26 |  | 0% | 2
1.4 | 2 | 완제품 출하 | 2 | 서지환 | 2023-01-25 | 2023-01-26 |  | 0% | 2
1.5 |  | 구매관리 | 4 |  | 2023-01-25 | 2023-01-26 |  |  | 4
1.5 | 1 | 자재 구매 입고 | 2 | 김재형 | 2023-01-25 | 2023-01-26 |  | 0% | 2
1.5 | 2 | 납품서 관리 | 2 | 정민영 | 2023-01-27 | 2023-01-30 |  | 0% | 2
1.6 |  | 품질 및 설비관리 | 6 |  | 2023-01-27 | 2023-02-03 |  |  | 6
1.6 | 1 | 검사 공정관계 설정 | 2 | 김민식 | 2023-01-31 | 2023-02-01 |  | 0% | 2
1.6 | 2 | 검사 데이터 입력 | 2 | 서지환 | 2023-01-27 | 2023-01-30 |  | 0% | 2
1.6 | 3 | 설비공정관계 | 2 | 김민식 | 2023-02-02 | 2023-02-03 |  | 0% | 2
1.7 |  | 프로그램 중간 테스트 | 2 |  | 2023-01-31 | 2023-02-06 |  |  | 2
1.7 | 1 | 기준정보관리 테스트 | 1 | 서지환 | 2023-01-31 | 2023-01-31 |  | 0% | 1
1.7 | 2 | MES기능 테스트 | 1 | 김민식 | 2023-02-06 | 2023-02-06 |  | 0% | 1
1.8 |  | 생산관리 POP | 19 |  | 2023-01-25 | 2023-02-16 |  |  | 19
1.8 | 1 | LOT생성 | 2 | 유기현 | 2023-01-25 | 2023-01-26 |  | 0% | 2
1.8 | 2 | 작업시작 | 2 | 유기현 | 2023-01-27 | 2023-01-30 |  | 0% | 2
1.8 | 3 | 자재사용 | 2 | 유기현 | 2023-01-31 | 2023-02-01 |  | 0% | 2
1.8 | 4 | 불량 등록 | 2 | 유기현 | 2023-02-02 | 2023-02-03 |  | 0% | 2
1.8 | 5 | 작업완료 | 3 | 유기현 | 2023-02-06 | 2023-02-08 |  | 0% | 3
1.8 | 6 | LOT상태조회 | 2 | 정민영 | 2023-01-31 | 2023-02-01 |  | 0% | 2
1.8 | 7 | LOT이력조회 | 2 | 정민영 | 2023-02-02 | 2023-02-03 |  | 0% | 2
1.8 | 8 | 불량 조회 | 2 | 서지환 | 2023-02-01 | 2023-02-02 |  | 0% | 2
1.8 | 9 | 설비 비가동 등록 | 2 | 서지환 | 2023-02-03 | 2023-02-06 |  | 0% | 2
1.9 |  | 리포트 - WEB | 7 |  | 2023-01-27 | 2023-02-01 |  |  | 7
1.9 | 1 | 계획대비 생산 실적 조회 | 2 | 김재형 | 2023-01-27 | 2023-01-30 |  | 0% | 2
1.9 | 2 | 제조 종합 효율 조회 | 2 | 김재형 | 2023-01-31 | 2023-02-01 |  | 0% | 2
1.9 | 3 | 검사 데이터 조회 | 1 | 김재형 | 2023-02-02 | 2023-02-02 |  | 0% | 1
1.9 | 4 | 생산 비가동 조회 | 2 | 김재형 | 2023-02-06 | 2023-02-07 |  | 0% | 2
2.0 |  | 프로그램 최종 테스트 | 6 |  | 2023-02-09 | 2023-02-16 |  |  | 6
2.0 | 1 | 모듈 간 연동 테스트 | 3 | 1조 전체 | 2023-02-09 | 2023-02-13 |  | 0% | 3
2.0 | 2 | 유효성 검사 및 버튼 기능 검사 | 3 | 1조 전체 | 2023-02-14 | 2023-02-16 |  | 0% | 3
Formulas:
Start Date = MIN([Start Date, row below]:F9)
Start Date = MIN([Start Date, row below]:[Start Date, row below])
Finish Date = MAX([Finish Date, row below]:G9)
Finish Date = IF([Days] >= 1, WORKDAY([Start Date],([Days] -1),L5:L30), WORKDAY([Start Date],[Days],L5:L30))
Note on K14: JH Kim: 공정코드 공정명 PR_1000 형상가공 PR_1100 내경가공 PR_1200 외경가공 PR_1300 절단가공 PR_2000 사출 PR_3000 조립_Dispenser PR_3100 조립_Body PR_3200 조립_Part1 PR_3300 조립_Part2
Note on K15: JH Kim: 창고 창고명 ST_1000 완제품창고 ST_0100 반제품창고 ST_0010 원자재창고
Note on K18: JH Kim: 설비 FC_SPLIT 절단 설비 FC_INCUT 내경 가공 FC_OUTCUT 외경 가공 FC_EJACULATION 사출 FC_ASSEMBLY_D DISPENSER 조립 FC_ASSEMBLY_B BODY 조립 FC_ASSEMBLY_M MAIN 부품 조립 FC_ASSEMBLY_S SUB 부품 조립
Note on K19: JH Kim: 검사항목코드 검사항목 IN_1001 치수검사 dispenser 내경(min : max : target : ) 외경(min : max : target : ) IN_1002 치수검사 cone 내경(min : max : target : ) IN_1003 치수검사 lead 외경(min : max : target : ) IN_2001 외관검사 sleeve, shaft (핀 홀 유/무) IN_3001 기능검사 (유/무)
Note on K24: JH Kim: 부서코드 부서명 DE_MANAGEMENT 관리팀 DE_PRODUCTION 생산관리팀 DE_MATERIAL 자재관리팀 DE_SALES 영업팀 DE_FACILITY 설비팀 DE_QUALITY 품질관리팀

## Summary
구디아카데미 멘토링 프로젝트 개발 일정
[6 empty] | 업데이트 | 2023-01-16
일정 종합
| Items |  | Issue Items | Complete Items | Estimation (M/D) | Remaining Efforts (M/D) | Progress (M/D) | Progress (%) | Developer | Issue Items | Complete Items | Estimation (M/D) | Remaining Efforts (M/D) | Progress (M/D) | Progress (%)
| Total |  | 35 | 4 | #N/A | #N/A | #N/A | #N/A | Total | 35 | 0 | 68 | 68 | 0 | 0%
| By Group | [7 empty] | By Developer
| WBS | Items | Issue Items | Complete Items | Estimation (M/D) | Remaining Efforts (M/D) | Progress (M/D) | Progress (%) | Developer | Issue Items | Complete Items | Estimation (M/D) | Remaining Efforts (M/D) | Progress (M/D) | Progress (%)
| 1.1 | 분석 설계 | 4 | 4 | 17 | 0 | 17 | 100% | 서지환 | 7 | 0 | 13 | 13 | 0 | 0%
| 1.2 | MES기준정보관리 | 9 | 0 | 16 | 16 | 0 | 0% | 김민식 | 7 | 0 | 13 | 13 | 0 | 0%
| 1.3 | 보안 | 4 | 0 | 8 | 8 | 0 | 0% | 유기현 | 7 | 0 | 15 | 15 | 0 | 0%
| 1.4 | 영업관리 | 2 | 0 | 4 | 4 | 0 | 0% | 정민영 | 7 | 0 | 14 | 14 | 0 | 0%
| 1.5 | 구매관리 | 2 | 0 | 4 | 4 | 0 | 0% | 김재형 | 7 | 0 | 13 | 13 | 0 | 0%
| 1.6 | 품질 및 설비관리 | 3 | 0 | 6 | 6 | 0 | 0% | x | 0 | 0 | 0 | 0 | 0 | 0%
| 1.7 | 프로그램 중간 테스트 | 2 | 0 | 2 | 2 | 0 | 0% | x | 0 | 0 | 0 | 0 | 0 | 0%
| 1.8 | 생산관리 POP | 9 | 0 | 19 | 19 | 0 | 0% | x | 0 | 0 | 0 | 0 | 0 | 0%
| 2.1 | #N/A | 0 | 0 | #N/A | #N/A | #N/A | #N/A
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%

## Developer
Developer List
Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer | Developer
서지환 | 김민식 | 유기현 | 정민영 | 김재형 | x | x | x